Supplier File Upload & Management Portal

Product Requirements Document with Phase-Wise Implementation Plan

Version: 2.0
Date: October 10, 2025
Project: Van Dyk Supplier Document Management System
Status: ✅ APPROVED FOR DEVELOPMENT
Total Timeline: 17 Weeks (~4 Months)

Table of Contents

- Executive Summary

- System Architecture Overview

- Core Requirements Summary

- Phase 1: Core Upload System (6 Weeks)

- Phase 2: File Management Interface (4 Weeks)

- Phase 3: Admin System (4 Weeks)

- Phase 4: Sync & Production Hardening (3 Weeks)

- Testing & Quality Assurance

- Deployment Checklist

- Appendix: Technical Specifications

1. Executive Summary

1.1 Product Vision

A web-based portal enabling suppliers to upload machine-related documentation packages directly to Van Dyk's Azure infrastructure with self-service file management capabilities and comprehensive admin moderation tools.

1.2 Key Features

- OTP-based authentication (no passwords)

- Unlimited file size uploads with chunking and resume

- Essential document validation (Manuals, Installation Drawings, Electrical Drawings)

- Supplier file management interface (browse, add, update, delete)

- Admin moderation and file movement capabilities

- Azure Files as source of truth with sync to Z:\FTProot

- Complete audit trail (permanent SQL logs)

- Admin email notifications

1.3 Success Metrics

- 95% uptime for upload portal

- Support 50 concurrent users

- 100% of operations logged in SQL

- Sync latency < 2 minutes to Z:\FTProot

- 80% reduction in supplier support requests

2. System Architecture Overview

2.1 Technology Stack

┌─────────────────────────────────────────────────────────────┐

│                     FRONTEND LAYER                          │

│  React.js + Material-UI + react-dropzone + react-pdf       │

│  Hosted on: Azure App Service (Linux)                      │

└─────────────────────────────────────────────────────────────┘

↓ HTTPS

┌─────────────────────────────────────────────────────────────┐

│                     BACKEND LAYER                           │

│  Python Flask API + SQLAlchemy                              │

│  Hosted on: Azure App Service (Linux B2)                   │

└─────────────────────────────────────────────────────────────┘

↓

┌──────────────────┴───────────────────┐

↓                                       ↓

┌──────────────────────┐          ┌──────────────────────────┐

│   AZURE FILES        │          │   AZURE SQL DATABASE     │

│  (SOURCE OF TRUTH)   │          │  Logs + Metadata         │

│  Premium Tier        │          │  Standard S2             │

└──────────────────────┘          └──────────────────────────┘

↓ Sync

┌──────────────────────┐          ┌──────────────────────────┐

│   Z:\FTProot         │          │   SENDGRID EMAIL         │

│  (Read-Only Replica) │          │   Admin Notifications    │

│  \\Vdbcwks0036\e\    │          └──────────────────────────┘

└──────────────────────┘

2.2 Data Flow

- Upload Flow: Supplier → React UI → Flask API → Azure Files → SQL Log → Sync to Z:\

- Browse Flow: Supplier → React UI → Flask API → Azure Files (read) → Display

- Update Flow: Supplier → React UI → Flask API → Azure Files (version) → SQL Log → Sync

- Admin Flow: Admin Portal → Flask API → Azure Files/SQL → Email Notification

2.3 Security Architecture

- All traffic over HTTPS (TLS 1.3)

- OTP authentication (6-digit, 10-minute expiry)

- Azure Key Vault for secrets

- Supplier ACL enforcement (access only own folders)

- Rate limiting (5 OTP/hour per email)

- SQL injection prevention (SQLAlchemy ORM)

3. Core Requirements Summary

3.1 User Roles

| Role | Capabilities |
| --- | --- |
| Supplier | Upload files, browse own projects, add/update/delete files, download files |
| Admin | View all uploads, moderate projects, move files, add notes, receive notifications, restore deleted files |

3.2 Essential Document Validation (WARNING Mode)

| Document Type | Keywords | Blocking? |
| --- | --- | --- |
| Manuals | manual, handbook, guide | ❌ WARNING ONLY |
| Installation Drawings | installation, install, drawing, dwg | ❌ WARNING ONLY |
| Electrical Drawings | electrical, schematic, wiring, diagram, elec | ❌ WARNING ONLY |

3.3 Key Business Rules

- Azure Files is source of truth - all operations write here first

- Z:\FTProot is read-only replica - updated via sync only

- Never permanently delete - all files retained as permanent log

- Admin moderates incorrect uploads - can move files between projects

- Email notifications to admin only - suppliers have web dashboard

- Validation is non-blocking - warnings displayed but upload proceeds

4. PHASE 1: Core Upload System (6 Weeks)

4.1 Phase 1 Objectives

- ✅ Establish authentication system

- ✅ Enable basic file uploads with metadata

- ✅ Store files in Azure Files

- ✅ Log all operations in SQL

- ✅ Implement essential document validation

4.2 Phase 1 Deliverables

- Working OTP authentication system

- Upload interface with chunking support

- Azure Files storage integration

- SQL database with core tables

- Validation engine (3 document types)

- Basic supplier dashboard

4.3 WEEK 1: Project Setup & Infrastructure

Backend Team TODO

- [ ] Set up Azure Resources

  - [ ] Create Azure Resource Group: vandyk-supplier-portal-prod

  - [ ] Provision Azure SQL Database (Standard S2)

    - Database name: VanDykSupplierPortal

    - Enable automated backups (7-day retention)

    - Configure firewall rules (Azure services + dev IPs)

  - [ ] Create Azure Files Storage Account

    - Account name: vandyksupplierdocs

    - Performance: Premium (for speed)

    - Redundancy: LRS or ZRS

    - Create file share: supplier-uploads

  - [ ] Set up Azure Key Vault

    - Vault name: vandyk-portal-kv

    - Store: SQL connection string, SendGrid API key, JWT secret

  - [ ] Configure Azure App Service (Linux B2)

    - Runtime: Python 3.11

    - Enable continuous deployment from GitHub

- [ ] Initialize Flask Project

  - [ ] Create project structure:

  - vandyk-supplier-portal/├── backend/│   ├── app/│   │   ├── __init__.py│   │   ├── models.py│   │   ├── routes/│   │   │   ├── auth.py│   │   │   ├── uploads.py│   │   │   └── admin.py│   │   ├── services/│   │   │   ├── azure_files.py│   │   │   ├── otp_service.py│   │   │   ├── validation_service.py│   │   │   └── email_service.py│   │   └── utils/│   │       ├── decorators.py│   │       └── helpers.py│   ├── migrations/│   ├── tests/│   ├── config.py│   ├── requirements.txt│   └── run.py

  - [ ] Set up dependencies in requirements.txt:

  - Flask==3.0.0Flask-SQLAlchemy==3.1.1Flask-CORS==4.0.0azure-storage-file-share==12.15.0azure-identity==1.15.0azure-keyvault-secrets==4.7.0pyodbc==5.0.1sendgrid==6.11.0pyjwt==2.8.0python-dotenv==1.0.0

  - [ ] Configure .env file structure

  - [ ] Set up logging (Winston/Python logging to Azure Application Insights)

- [ ] Database Schema Design & Migration

  - [ ] Create SQL migration scripts:

    - 001_create_suppliers_table.sql

    - 002_create_uploads_table.sql

    - 003_create_file_operation_log.sql

    - 004_create_otp_tokens_table.sql

  - [ ] Suppliers Table:

  - CREATE TABLE Suppliers (    SupplierID INT PRIMARY KEY IDENTITY(1,1),    SupplierName NVARCHAR(200) NOT NULL,    SupplierType NVARCHAR(100) NOT NULL,    ContactEmail NVARCHAR(255) NOT NULL UNIQUE,    SecondaryEmails NVARCHAR(MAX), -- JSON array    AzureFolderPath NVARCHAR(500) NOT NULL,    CreatedDate DATETIME DEFAULT GETDATE(),    IsActive BIT DEFAULT 1,    LastLoginDate DATETIME);

  - [ ] SupplierUploads Table:

  - CREATE TABLE SupplierUploads (    UploadID INT PRIMARY KEY IDENTITY(1,1),    SupplierID INT FOREIGN KEY REFERENCES Suppliers(SupplierID),    SupplierEmail NVARCHAR(255),    ProjectNumber NVARCHAR(50) NOT NULL,    ProjectName NVARCHAR(200) NOT NULL,    FolderPath NVARCHAR(500),    UploadStartTime DATETIME,    UploadCompleteTime DATETIME,    FileCount INT,    TotalSizeMB DECIMAL(10,2),    HasManuals BIT,    HasInstallationDrawings BIT,    HasElectricalDrawings BIT,    ValidationReport NVARCHAR(MAX),    Status NVARCHAR(50) DEFAULT 'InProgress',    SyncedToFTPRoot BIT DEFAULT 0,    SyncTimestamp DATETIME,    AdminModerated BIT DEFAULT 0,    AdminNotes NVARCHAR(MAX));

  - [ ] FileOperationLog Table:

  - CREATE TABLE FileOperationLog (    OperationID INT PRIMARY KEY IDENTITY(1,1),    UploadID INT FOREIGN KEY REFERENCES SupplierUploads(UploadID),    SupplierID INT FOREIGN KEY REFERENCES Suppliers(SupplierID),    OperationType NVARCHAR(50) NOT NULL, -- Add, Update, Delete, Replace    FileName NVARCHAR(500),    FilePath NVARCHAR(1000),    FileSize BIGINT,    PreviousVersionPath NVARCHAR(1000),    OperationTimestamp DATETIME DEFAULT GETDATE(),    PerformedBy NVARCHAR(255),    IsActive BIT DEFAULT 1);

  - [ ] OTPTokens Table:

  - CREATE TABLE OTPTokens (    TokenID INT PRIMARY KEY IDENTITY(1,1),    Email NVARCHAR(255) NOT NULL,    OTPCode NCHAR(6) NOT NULL,    CreatedAt DATETIME DEFAULT GETDATE(),    ExpiresAt DATETIME NOT NULL,    IsUsed BIT DEFAULT 0,    AttemptCount INT DEFAULT 0);

  - [ ] Run migrations on Azure SQL

  - [ ] Create indexes on frequently queried columns

Frontend Team TODO

- [ ] Set up React Project

  - [ ] Initialize React app: npx create-react-app frontend

  - [ ] Install dependencies:

  - npm install @mui/material @emotion/react @emotion/stylednpm install react-router-dom axiosnpm install react-dropzonenpm install @mui/icons-material

  - [ ] Set up project structure:

  - frontend/├── src/│   ├── components/│   │   ├── Auth/│   │   │   ├── LoginForm.jsx│   │   │   └── OTPVerification.jsx│   │   ├── Upload/│   │   │   ├── UploadForm.jsx│   │   │   ├── FileDropzone.jsx│   │   │   └── ProgressBar.jsx│   │   ├── Dashboard/│   │   │   └── SupplierDashboard.jsx│   │   └── Common/│   │       ├── Header.jsx│   │       └── Footer.jsx│   ├── services/│   │   ├── api.js│   │   └── authService.js│   ├── contexts/│   │   └── AuthContext.js│   ├── utils/│   │   └── helpers.js│   └── App.js

  - [ ] Configure environment variables (.env)

  - [ ] Set up ESLint and Prettier

- [ ] Design UI/UX Mockups

  - [ ] Login page wireframe

  - [ ] OTP verification page wireframe

  - [ ] Dashboard layout wireframe

  - [ ] Upload form wireframe

  - [ ] Validation results page wireframe

  - [ ] Get stakeholder approval on designs

DevOps TODO

- [ ] Set up GitHub repository with main/dev branches

- [ ] Configure GitHub Actions CI/CD pipeline

- [ ] Set up staging environment (separate Azure App Service)

- [ ] Configure Application Insights for monitoring

- [ ] Set up alerts for critical errors

Week 1 Milestone: Infrastructure provisioned, projects initialized, database schema created

4.4 WEEK 2: Authentication System

Backend Team TODO

- [ ] Implement OTP Service (services/otp_service.py)

  - [ ] Generate 6-digit random OTP using secrets module

  - [ ] Store OTP in database with expiration (10 minutes)

  - [ ] Implement rate limiting: max 5 OTP requests per hour per email

  - [ ] Create OTP cleanup job (delete expired tokens)

  - [ ] Functions:

  - def generate_otp(email: str) -> strdef verify_otp(email: str, code: str) -> booldef check_rate_limit(email: str) -> bool

- [ ] Implement Email Service (services/email_service.py)

  - [ ] Integrate SendGrid API

  - [ ] Create OTP email template (HTML + plain text)

  - [ ] Function: send_otp_email(email: str, otp: str) -> bool

  - [ ] Handle email delivery failures gracefully

  - [ ] Log all email attempts

- [ ] Authentication Routes (routes/auth.py)

  - [ ] POST /api/auth/request-otp

    - Validate email format

    - Check if email exists in Suppliers table

    - Check rate limit

    - Generate and send OTP

    - Return success/error response

  - [ ] POST /api/auth/verify-otp

    - Validate OTP code

    - Check expiration

    - Increment attempt count (max 3 attempts)

    - Generate JWT token on success (24-hour expiry)

    - Update LastLoginDate in Suppliers table

  - [ ] POST /api/auth/logout

    - Invalidate JWT token (add to blacklist table)

- [ ] JWT Token Management

  - [ ] Create JWT token with payload: {supplierID, email, supplierType}

  - [ ] Implement token verification middleware

  - [ ] Create decorator: @require_auth for protected routes

  - [ ] Handle token expiration and refresh

- [ ] Seed Test Data

  - [ ] Insert 5 test suppliers into database:

  - INSERT INTO Suppliers VALUES ('ABC Mechanical Equipment', 'Mechanical Equipment Supplier', 'supplier1@test.com', NULL, '/ABC_Mechanical/', GETDATE(), 1, NULL),('XYZ Electrical Systems', 'Electrical Systems Supplier', 'supplier2@test.com', NULL, '/XYZ_Electrical/', GETDATE(), 1, NULL),('DEF Controls', 'Controls & Instrumentation Supplier', 'supplier3@test.com', NULL, '/DEF_Controls/', GETDATE(), 1, NULL);

  - [ ] Create corresponding folders in Azure Files

Frontend Team TODO

- [ ] Build Login Page (components/Auth/LoginForm.jsx)

  - [ ] Email input field with validation

  - [ ] "Send OTP" button

  - [ ] Loading state during API call

  - [ ] Error message display

  - [ ] Success message: "OTP sent to your email"

  - [ ] Integrate with API: POST /api/auth/request-otp

- [ ] Build OTP Verification Page (components/Auth/OTPVerification.jsx)

  - [ ] 6-digit OTP input (auto-focus, auto-advance)

  - [ ] "Verify" button

  - [ ] Countdown timer (10 minutes)

  - [ ] "Resend OTP" link

  - [ ] Error handling (invalid OTP, expired, max attempts)

  - [ ] Integrate with API: POST /api/auth/verify-otp

  - [ ] Store JWT token in localStorage/sessionStorage

  - [ ] Redirect to dashboard on success

- [ ] Create Auth Context (contexts/AuthContext.js)

  - [ ] Manage authentication state (logged in, user info)

  - [ ] Provide auth methods: login(), logout(), checkAuth()

  - [ ] Protected route wrapper component

- [ ] API Service Layer (services/api.js)

  - [ ] Configure Axios with base URL

  - [ ] Request interceptor: attach JWT token to headers

  - [ ] Response interceptor: handle 401 errors (redirect to login)

Testing TODO

- [ ] Test OTP generation (verify randomness, no duplicates)

- [ ] Test rate limiting (5 requests/hour enforcement)

- [ ] Test OTP expiration (10 minutes)

- [ ] Test invalid email (not in Suppliers table)

- [ ] Test invalid OTP (3 attempts then lockout)

- [ ] Test JWT token generation and verification

- [ ] Manual UI testing: login flow end-to-end

Week 2 Milestone: Working authentication system with OTP

4.5 WEEK 3: Azure Files Integration & File Upload Backend

Backend Team TODO

- [ ] Azure Files Service (services/azure_files.py)

  - [ ] Initialize Azure File Share client using connection string from Key Vault

  - [ ] Implement folder creation:

  - def create_supplier_folder(supplier_name: str) -> strdef create_project_folder(supplier_path: str, project_number: str, project_name: str) -> str

  - [ ] Implement file upload with chunking:

  - def upload_file_chunk(file_path: str, chunk_data: bytes, offset: int) -> booldef finalize_upload(file_path: str) -> bool

  - [ ] Implement folder listing:

  - def list_files(folder_path: str) -> List[Dict]

  - [ ] Handle Azure Files errors gracefully

  - [ ] Add retry logic (3 attempts with exponential backoff)

- [ ] Upload Routes (routes/uploads.py)

  - [ ] POST /api/uploads/initiate

    - Accept: projectNumber, projectName

    - Validate project metadata

    - Sanitize folder name (remove special chars)

    - Check for duplicate project number

    - Create project folder in Azure Files

    - Create upload record in SupplierUploads table (Status='InProgress')

    - Return uploadID and upload URL

  - [ ] POST /api/uploads/chunk/{uploadId}

    - Accept: file chunk (multipart form data), chunkIndex, totalChunks, fileName

    - Validate uploadId and supplier ownership

    - Write chunk to Azure Files

    - Track progress in database

    - Return success + progress percentage

  - [ ] POST /api/uploads/complete/{uploadId}

    - Finalize all file uploads

    - Update FileCount and TotalSizeMB

    - Trigger validation scan

    - Update Status='Completed'

    - Return validation results

- [ ] Chunked Upload Logic

  - [ ] Split large files into 5MB chunks

  - [ ] Store chunk metadata in temporary table

  - [ ] Assemble chunks on completion

  - [ ] Clean up temporary data

- [ ] File List Generation

  - [ ] Recursively scan all files in uploaded folder

  - [ ] Store file list as JSON in FileOperationLog

  - [ ] Format: [{"name": "file.pdf", "size": 1234567, "path": "/folder/file.pdf"}]

Frontend Team TODO

- [ ] Build Upload Form (components/Upload/UploadForm.jsx)

  - [ ] Project Number input (required, alphanumeric, max 50 chars)

  - [ ] Project Name input (required, max 200 chars)

  - [ ] Form validation

  - [ ] "Next" button to proceed to file selection

- [ ] Build File Dropzone (components/Upload/FileDropzone.jsx)

  - [ ] Integrate react-dropzone

  - [ ] Support folder upload (maintain directory structure)

  - [ ] Display selected files with sizes

  - [ ] "Remove" button for each file

  - [ ] Total size calculator

  - [ ] "Start Upload" button

- [ ] Build Progress Bar (components/Upload/ProgressBar.jsx)

  - [ ] File-by-file progress display

  - [ ] Overall upload progress (percentage)

  - [ ] Cancel upload button

  - [ ] Estimated time remaining

  - [ ] Success/error messages per file

- [ ] Implement Chunked Upload Client

  - [ ] Split files into 5MB chunks

  - [ ] Upload chunks sequentially with retry on failure

  - [ ] Resume capability (store last uploaded chunk in localStorage)

  - [ ] Call /api/uploads/initiate first

  - [ ] Loop through files and chunks: POST /api/uploads/chunk/{uploadId}

  - [ ] Call /api/uploads/complete/{uploadId} when done

Testing TODO

- [ ] Test folder creation in Azure Files

- [ ] Test single file upload (< 10MB)

- [ ] Test large file upload (> 1GB) with chunking

- [ ] Test upload resume after network interruption

- [ ] Test folder upload with nested directories

- [ ] Test concurrent uploads (5 files simultaneously)

- [ ] Test upload cancellation

Week 3 Milestone: Files successfully uploading to Azure Files with chunking

4.6 WEEK 4: Validation Engine

Backend Team TODO

- [ ] Validation Service (services/validation_service.py)

  - [ ] Implement keyword matching function:

  - def scan_for_keywords(filename: str, keywords: List[str]) -> bool:    """Case-insensitive search for any keyword in filename"""    filename_lower = filename.lower()    return any(keyword.lower() in filename_lower for keyword in keywords)

  - [ ] Define validation rules:

  - VALIDATION_RULES = {    'manuals': ['manual', 'handbook', 'guide'],    'installationDrawings': ['installation', 'install', 'drawing', 'dwg'],    'electricalDrawings': ['electrical', 'schematic', 'wiring', 'diagram', 'elec']}

  - [ ] Implement validation scanner:

  - def validate_upload(upload_id: int) -> Dict:    # Get all files for this upload from Azure Files    # Scan each filename against validation rules    # Return results: {check_name: {status: FOUND/MISSING, matchedFiles: []}}

  - [ ] Generate validation report (JSON format)

  - [ ] Store report in SupplierUploads.ValidationReport

  - [ ] Update HasManuals, HasInstallationDrawings, HasElectricalDrawings flags

- [ ] Integrate Validation into Upload Flow

  - [ ] Call validate_upload() in POST /api/uploads/complete

  - [ ] Return validation results in API response

  - [ ] Ensure validation never blocks upload (WARNING mode)

- [ ] Validation Report Schema

- {

- "uploadId": 12345,

- "timestamp": "2025-10-10T14:30:00Z",

- "filesScanned": 47,

- "checks": {

- "manuals": {

- "status": "FOUND",

- "matchedFiles": ["User_Manual_v2.pdf", "Maintenance_Guide.pdf"]

- },

- "installationDrawings": {

- "status": "FOUND",

- "matchedFiles": ["Installation_Layout.dwg"]

- },

- "electricalDrawings": {

- "status": "MISSING",

- "matchedFiles": []

- }

- },

- "overallStatus": "WARNING"

- }

Frontend Team TODO

- [ ] Build Validation Results Page (components/Upload/ValidationResults.jsx)

  - [ ] Display validation summary:

    - ✅ Manuals Found (2 files)

    - ✅ Installation Drawings Found (1 file)

    - ❌ Electrical Drawings Missing

  - [ ] Show matched filenames for each category

  - [ ] Warning banner if any checks fail (but allow proceed)

  - [ ] "View Files" button to expand matched files list

  - [ ] "Confirm & Finish" button

  - [ ] "Upload More Files" button (to add missing documents)

- [ ] Visual Design for Validation

  - [ ] Green checkmark for FOUND

  - [ ] Red X with yellow warning banner for MISSING

  - [ ] Collapsible sections for file lists

  - [ ] Clear messaging: "Your upload is complete. However, we noticed..."

Testing TODO

- [ ] Test validation with all documents present

- [ ] Test validation with missing manuals

- [ ] Test validation with no matching files

- [ ] Test case-insensitive keyword matching

- [ ] Test special characters in filenames

- [ ] Test validation performance (1000+ files)

- [ ] Verify validation report JSON format

Week 4 Milestone: Validation engine working, results displayed to user

4.7 WEEK 5: Supplier Dashboard & Upload History

Backend Team TODO

- [ ] Upload History Route (routes/uploads.py)

  - [ ] GET /api/uploads/history

    - Filter by logged-in supplier (from JWT)

    - Return list of all uploads with metadata

    - Include validation status

    - Sort by UploadCompleteTime DESC

    - Response format:

  - [

  - {

  - "uploadId": 123,

  - "projectNumber": "WM001",

  - "projectName": "Placer County MRF",

  - "uploadDate": "2025-10-10T14:30:00Z",

  - "fileCount": 47,

  - "totalSizeMB": 2345.67,

  - "validationStatus": "WARNING",

  - "hasManuals": true,

  - "hasInstallationDrawings": true,

  - "hasElectricalDrawings": false

  - }

  - ]

- [ ] GET /api/uploads/{uploadId}/details

  - Return detailed upload information

  - Include file list

  - Include validation report

  - Verify supplier owns this upload

Frontend Team TODO

- [ ] Build Supplier Dashboard (components/Dashboard/SupplierDashboard.jsx)

  - [ ] Welcome message: "Welcome back, [Supplier Name]!"

  - [ ] "New Upload" button (prominent, top-right)

  - [ ] Upload history table with columns:

    - Project Number

    - Project Name

    - Upload Date

    - File Count

    - Size

    - Validation Status (icon + tooltip)

    - Actions (View Details)

  - [ ] Search/filter by project number or name

  - [ ] Pagination (10 uploads per page)

  - [ ] Empty state: "No uploads yet. Click New Upload to get started."

- [ ] Build Upload Details Modal

  - [ ] Display complete upload metadata

  - [ ] Show validation results

  - [ ] List all files with sizes

  - [ ] "Download All" button (future: Phase 2)

  - [ ] "Add Files to This Project" button (future: Phase 2)

- [ ] Navigation & Layout

  - [ ] Header with logo, supplier name, logout button

  - [ ] Sidebar navigation (Dashboard, New Upload)

  - [ ] Responsive design (mobile-friendly)

Testing TODO

- [ ] Test dashboard loads correctly

- [ ] Test upload history retrieval

- [ ] Test filtering and search

- [ ] Test pagination

- [ ] Test upload details modal

- [ ] Test UI on mobile devices

Week 5 Milestone: Supplier can view all past uploads in dashboard

4.8 WEEK 6: Phase 1 Testing & Bug Fixes

All Teams TODO

- [ ] End-to-End Testing

  - [ ] Test complete upload flow: login → upload → validation → dashboard

  - [ ] Test with 5 different test suppliers

  - [ ] Upload variety of file types (PDF, DWG, DOCX, XLSX)

  - [ ] Test with small files (< 1MB) and large files (> 5GB)

  - [ ] Test network interruption scenarios

- [ ] Security Testing

  - [ ] Penetration testing (OWASP Top 10)

  - [ ] SQL injection attempts

  - [ ] JWT token tampering

  - [ ] Cross-supplier access attempts (ensure ACL works)

  - [ ] Rate limiting verification

  - [ ] HTTPS/TLS configuration check

- [ ] Performance Testing

  - [ ] Load test: 50 concurrent users

  - [ ] Upload stress test: Multiple 10GB files

  - [ ] Database query optimization (check slow queries)

  - [ ] Azure Files throughput test

- [ ] Bug Fixes & Polish

  - [ ] Fix all P0/P1 bugs discovered in testing

  - [ ] Improve error messages

  - [ ] Add loading spinners where needed

  - [ ] Optimize API response times

  - [ ] Fix any UI/UX issues

- [ ] Documentation

  - [ ] API documentation (Swagger/OpenAPI)

  - [ ] Deployment guide

  - [ ] Supplier user guide (how to upload)

  - [ ] Troubleshooting guide

Phase 1 Complete: ✅ Core upload system functional and tested

Phase 1 Demo Checklist:

- [ ] Supplier can log in with OTP

- [ ] Supplier can upload files (any size)

- [ ] Files stored in Azure Files

- [ ] Validation runs and displays results

- [ ] Upload logged in SQL

- [ ] Dashboard shows upload history

5. PHASE 2: File Management Interface (4 Weeks)

5.1 Phase 2 Objectives

- ✅ Enable suppliers to browse uploaded files

- ✅ Allow adding files to existing projects

- ✅ Implement file versioning (replace files)

- ✅ Soft delete functionality

- ✅ Download files

5.2 Phase 2 Deliverables

- Web-based file browser

- File upload to existing projects

- File versioning system

- Soft delete with admin restore

- Download functionality

5.3 WEEK 7: File Browser Backend

Backend Team TODO

- [ ] File Management Routes (routes/projects.py - new file)

  - [ ] GET /api/projects

    - List all projects for logged-in supplier

    - Return: projectId, projectNumber, projectName, folderPath, fileCount, totalSize, lastModified

  - [ ] GET /api/projects/{projectId}/files

    - List all files in project folder (recursive)

    - Return file tree structure with metadata

    - Response format:

  - {

  - "projectId": 123,

  - "files": [

  - {

  - "fileId": 456,

  - "name": "Manual.pdf",

  - "path": "/WM001_PlacerMRF/Manual.pdf",

  - "size": 1234567,

  - "uploadDate": "2025-10-10T14:30:00Z",

  - "isActive": true,

  - "version": 1

  - }

  - ]

  - }

  - [ ] GET /api/projects/{projectId}/files/{fileId}

    - Get single file metadata

    - Verify supplier ownership

- [ ] File Metadata System

  - [ ] Enhance FileOperationLog to store full file metadata

  - [ ] Create file ID system (hash or UUID)

  - [ ] Store file relationships (versions)

- [ ] Azure Files Directory Listing

  - [ ] Implement recursive directory traversal

  - [ ] Cache file listings (refresh every 5 minutes)

  - [ ] Handle large directories (1000+ files)

Testing TODO

- [ ] Test project listing

- [ ] Test file listing with nested folders

- [ ] Test with large number of files (500+)

- [ ] Test file metadata accuracy

- [ ] Verify supplier ACL (can't access other supplier's files)

Week 7 Milestone: Backend API for file browsing complete

5.4 WEEK 8: File Browser Frontend

Frontend Team TODO

- [ ] Build File Browser Component (components/Projects/FileBrowser.jsx)

  - [ ] Tree view for nested folders

  - [ ] File list with columns: Name, Size, Upload Date, Actions

  - [ ] Icons for different file types (PDF, DWG, etc.)

  - [ ] Folder expand/collapse functionality

  - [ ] Breadcrumb navigation

  - [ ] "Back to Projects" button

- [ ] File Actions Menu

  - [ ] Right-click context menu or action buttons:

    - Download

    - Replace

    - Delete

    - View Details

  - [ ] Confirmation dialogs for destructive actions

- [ ] Project View Page (pages/ProjectView.jsx)

  - [ ] Project header: Number, Name, Total Size

  - [ ] "Add Files" button

  - [ ] File browser component

  - [ ] Validation status summary (from Phase 1)

- [ ] Performance Optimization

  - [ ] Virtual scrolling for large file lists (react-window)

  - [ ] Lazy loading of folder contents

  - [ ] Skeleton loading states

Testing TODO

- [ ] Test file browser with small projects (< 10 files)

- [ ] Test with large projects (1000+ files)

- [ ] Test nested folder navigation

- [ ] Test file actions menu

- [ ] Test UI responsiveness

Week 8 Milestone: Suppliers can browse their uploaded files

5.5 WEEK 9: File Operations (Add, Replace, Delete)

Backend Team TODO

- [ ] Add Files to Existing Project

  - [ ] POST /api/projects/{projectId}/files/upload

    - Reuse chunked upload logic from Phase 1

    - Append files to existing folder in Azure Files

    - Log operation in FileOperationLog (OperationType='Add')

    - Re-run validation scan

    - Update SupplierUploads.FileCount and TotalSizeMB

- [ ] Replace File (Versioning)

  - [ ] PUT /api/projects/{projectId}/files/{fileId}

    - Check if filename already exists

    - If exists:

      - Rename current file: file.pdf → file_v1.pdf

      - Move to _archive/ subfolder

      - Upload new file as file.pdf

      - Increment version number in FileOperationLog

      - Store PreviousVersionPath

    - Log operation (OperationType='Replace')

    - Return new file metadata

- [ ] Soft Delete File

  - [ ] DELETE /api/projects/{projectId}/files/{fileId}

    - Move file to _deleted/ subfolder in Azure Files

    - Set IsActive=FALSE in FileOperationLog

    - Do NOT permanently delete

    - Log operation (OperationType='Delete')

    - Update FileCount in SupplierUploads

    - Re-run validation if deleted file was in validation results

- [ ] Version Management

  - [ ] Create _archive/ folder structure in Azure Files

  - [ ] Store version metadata in SQL

  - [ ] Implement version listing: GET /api/projects/{projectId}/files/{fileId}/versions

Frontend Team TODO

- [ ] Add Files UI

  - [ ] Reuse FileDropzone from Phase 1

  - [ ] "Add Files to [Project Name]" modal

  - [ ] Upload progress display

  - [ ] Refresh file list after upload

- [ ] Replace File UI

  - [ ] Upload interface with "Replace" button

  - [ ] Warning: "This will create a new version. Old file will be archived."

  - [ ] Confirmation dialog

  - [ ] Show version history

- [ ] Delete File UI

  - [ ] Confirmation dialog: "Are you sure? Admins can restore this file within 30 days."

  - [ ] Remove file from list after deletion

  - [ ] Show success toast

- [ ] Version History Modal

  - [ ] List all versions of a file

  - [ ] Show version number, date, uploaded by

  - [ ] "Download" button for each version

  - [ ] "Restore This Version" (creates new version with old content)

Testing TODO

- [ ] Test adding files to existing project

- [ ] Test replacing file (verify versioning)

- [ ] Test deleting file (verify soft delete)

- [ ] Test version history display

- [ ] Verify validation re-runs after file operations

- [ ] Test with multiple file types

Week 9 Milestone: Full CRUD operations on files working

5.6 WEEK 10: Download & Phase 2 Testing

Backend Team TODO

- [ ] File Download

  - [ ] GET /api/projects/{projectId}/files/{fileId}/download

    - Generate pre-signed URL from Azure Files (1-hour expiry)

    - Or stream file directly through Flask

    - Log download in FileOperationLog (OperationType='Download')

    - Return file with correct MIME type

- [ ] Folder Download (ZIP)

  - [ ] GET /api/projects/{projectId}/download-all

    - Create temporary ZIP archive

    - Include all active files (exclude _deleted, _archive)

    - Stream ZIP to user

    - Clean up temp file after download

    - Handle large folders (> 5GB)

- [ ] Validation Re-scan

  - [ ] Automatically trigger validation after file add/delete

  - [ ] Update validation status in real-time

  - [ ] API endpoint: POST /api/projects/{projectId}/validate

Frontend Team TODO

- [ ] Download Functionality

  - [ ] Single file download button

  - [ ] "Download All" button (generates ZIP)

  - [ ] Progress indicator for large downloads

  - [ ] Handle download errors gracefully

- [ ] Real-time Validation Updates

  - [ ] After file operations, fetch updated validation status

  - [ ] Display updated validation results

  - [ ] Show "Validation in progress..." spinner

Testing TODO

- [ ] Complete Phase 2 Testing

  - [ ] Test all file operations end-to-end

  - [ ] Test downloading single files

  - [ ] Test downloading entire projects (ZIP)

  - [ ] Test version management

  - [ ] Test soft delete and restore (backend only for now)

  - [ ] Performance test with large files

  - [ ] Test concurrent file operations

- [ ] User Acceptance Testing

  - [ ] Get 3 test suppliers to use the system

  - [ ] Collect feedback

  - [ ] Fix critical bugs

Phase 2 Complete: ✅ Suppliers can fully manage their files

Phase 2 Demo Checklist:

- [ ] Supplier can browse files

- [ ] Supplier can add files to existing project

- [ ] Supplier can replace files (versioning works)

- [ ] Supplier can delete files (soft delete)

- [ ] Supplier can download files

- [ ] Validation updates after file changes

6. PHASE 3: Admin System (4 Weeks)

6.1 Phase 3 Objectives

- ✅ Build admin authentication and portal

- ✅ Implement admin monitoring dashboard

- ✅ Enable file movement between projects

- ✅ Add admin notes and moderation

- ✅ Set up email notifications

6.2 Phase 3 Deliverables

- Admin login system

- Admin dashboard with all uploads

- File movement tool

- Admin moderation interface

- Email notification system

- Audit trail viewer

6.3 WEEK 11: Admin Authentication & Dashboard Backend

Backend Team TODO

- [ ] Admin Users Table

- CREATE TABLE AdminUsers (

- AdminID INT PRIMARY KEY IDENTITY(1,1),

- Email NVARCHAR(255) NOT NULL UNIQUE,

- FullName NVARCHAR(200),

- ReceiveUploadNotifications BIT DEFAULT 1,

- ReceiveSyncFailureNotifications BIT DEFAULT 1,

- NotificationFrequency NVARCHAR(50) DEFAULT 'Immediate',

- CreatedDate DATETIME DEFAULT GETDATE(),

- IsActive BIT DEFAULT 1

- );

  - [ ] Seed admin users (3-5 Van Dyk staff)

- [ ] Admin Authentication

  - [ ] Reuse OTP system but separate admin login route

  - [ ] POST /api/admin/auth/request-otp

  - [ ] POST /api/admin/auth/verify-otp

  - [ ] Generate admin JWT with role: {adminID, email, role: 'admin'}

  - [ ] Create middleware: @require_admin

- [ ] Admin Dashboard Routes (routes/admin.py)

  - [ ] GET /api/admin/uploads

    - Return ALL uploads across ALL suppliers

    - Support filters: supplierID, projectNumber, dateRange, validationStatus, moderatedStatus

    - Support sorting: uploadDate, fileCount, size

    - Pagination (20 per page)

    - Response includes supplier name, project info, validation status

  - [ ] GET /api/admin/uploads/{uploadId}

    - Detailed view of single upload

    - Include file list, validation report, admin notes, operation history

  - [ ] GET /api/admin/stats

    - Dashboard statistics:

      - Total uploads today/week/month

      - Total storage used

      - Uploads by supplier

      - Validation status distribution

      - Unreviewed uploads count

Testing TODO

- [ ] Test admin login

- [ ] Test admin can access all supplier data

- [ ] Test filters and sorting

- [ ] Test dashboard stats accuracy

Week 11 Milestone: Admin can log in and view all uploads

6.4 WEEK 12: Admin Dashboard Frontend & Moderation Tools

Frontend Team TODO

- [ ] Build Admin Login Page

  - [ ] Separate admin portal route: /admin

  - [ ] Same OTP flow as supplier login

  - [ ] Different branding/theme for admin

- [ ] Build Admin Dashboard (components/Admin/AdminDashboard.jsx)

  - [ ] Stats cards at top:

    - Total Uploads Today

    - Unreviewed Uploads

    - Total Storage Used

    - Active Suppliers

  - [ ] Upload table with columns:

    - Upload ID

    - Supplier Name

    - Project Number

    - Project Name

    - Upload Date

    - File Count

    - Size

    - Validation Status

    - Moderated (✓/✗)

    - Actions

  - [ ] Filters:

    - Supplier dropdown

    - Date range picker

    - Validation status filter

    - Moderated/Unreviewed filter

  - [ ] Search by project number

  - [ ] Pagination

- [ ] Build Upload Details Modal (components/Admin/UploadDetailsModal.jsx)

  - [ ] All upload metadata

  - [ ] File list with file browser

  - [ ] Validation results

  - [ ] Admin notes section (editable)

  - [ ] "Mark as Reviewed" button

  - [ ] File operation history

  - [ ] Action buttons:

    - Move Files

    - Re-run Validation

    - Trigger Sync

Backend Team TODO

- [ ] Admin Moderation Routes

  - [ ] POST /api/admin/uploads/{uploadId}/moderate

    - Add/update admin notes

    - Mark as reviewed (AdminModerated=TRUE)

    - Log who reviewed and when

  - [ ] GET /api/admin/uploads/{uploadId}/audit-trail

    - Return complete operation history from FileOperationLog

    - Include: all file operations, uploads, modifications, deletions

Testing TODO

- [ ] Test admin dashboard loads

- [ ] Test filters work correctly

- [ ] Test search functionality

- [ ] Test upload details modal

- [ ] Test adding admin notes

Week 12 Milestone: Admin dashboard functional with moderation

6.5 WEEK 13: File Movement & Advanced Admin Tools

Backend Team TODO

- [ ] Move Files Between Projects

  - [ ] POST /api/admin/files/move

    - Parameters: fileId, sourceProjectId, targetProjectId

    - Validate both projects exist

    - Move file in Azure Files from source to target folder

    - Update FileOperationLog (OperationType='AdminMove')

    - Update file counts in both SupplierUploads records

    - Re-run validation for both projects

    - Log admin who performed move

- [ ] Restore Deleted Files

  - [ ] POST /api/admin/files/{fileId}/restore

    - Move file from _deleted/ back to project folder

    - Set IsActive=TRUE in FileOperationLog

    - Log operation (OperationType='AdminRestore')

    - Re-run validation

- [ ] Manual Validation Trigger

  - [ ] POST /api/admin/uploads/{uploadId}/validate

    - Re-run validation scan

    - Update validation results

    - Return new validation report

- [ ] Manual Sync Trigger

  - [ ] POST /api/admin/uploads/{uploadId}/sync

    - Force sync to Z:\FTProot

    - Return sync status

    - Log sync attempt

Frontend Team TODO

- [ ] Build Move Files Tool (components/Admin/MoveFilesTool.jsx)

  - [ ] Select files from source project

  - [ ] Search for target project (by project number or name)

  - [ ] Preview move (show source → target)

  - [ ] Confirmation dialog

  - [ ] Execute move

  - [ ] Show success message

- [ ] Build Restore Files Interface

  - [ ] In upload details, show "Deleted Files" tab

  - [ ] List soft-deleted files

  - [ ] "Restore" button for each file

  - [ ] Confirmation dialog

- [ ] Admin Action Buttons

  - [ ] "Move Files" button in upload details

  - [ ] "Restore Deleted Files" button

  - [ ] "Re-run Validation" button

  - [ ] "Trigger Sync" button

Testing TODO

- [ ] Test moving single file

- [ ] Test moving multiple files

- [ ] Test moving files updates file counts

- [ ] Test validation re-runs after move

- [ ] Test restoring deleted files

- [ ] Test manual validation trigger

- [ ] Test manual sync trigger

Week 13 Milestone: Admin can move files and restore deleted files

6.6 WEEK 14: Email Notification System & Phase 3 Testing

Backend Team TODO

- [ ] Email Notification Service (services/notification_service.py)

  - [ ] Function: notify_admins_new_upload(upload_id: int)

  - [ ] Function: notify_admins_sync_failure(upload_id: int, error: str)

  - [ ] Email templates:

    - New Upload Notification (HTML + plain text)

    - Sync Failure Alert

  - [ ] Query AdminUsers table for notification preferences

  - [ ] Send via SendGrid

  - [ ] Log all email attempts in database

- [ ] Email Templates

  - [ ] New Upload Notification:

  - Subject: New Supplier Upload - [ProjectNo] [ProjectName]

  - Supplier: [Supplier Name]

  - Project: [ProjectNo] - [ProjectName]

  - Upload Time: [DateTime]

  - Files: [Count] files, [Size] GB

  - Validation Status:

  - ✓ Manuals Found

  - ✓ Installation Drawings Found

  - ✗ Electrical Drawings Missing (WARNING)

  - View Upload: [Link to admin portal]

  - [ ] Sync Failure Alert:

  - Subject: ALERT: Sync Failed for Upload #[UploadID]

  - Project: [ProjectNo] - [ProjectName]

  - Supplier: [Supplier Name]

  - Error: [Error Message]

  - Retry Attempts: [Count]

  - Action Required: Please review and manually trigger sync.

  - View Details: [Link]

- [ ] Integrate Notifications

  - [ ] Call notify_admins_new_upload() in POST /api/uploads/complete

  - [ ] Call after upload completes and validation runs

  - [ ] Use background task/queue (celery or simple threading)

  - [ ] Don't block upload completion waiting for email

- [ ] Notification Preferences API

  - [ ] GET /api/admin/profile/notifications

  - [ ] PUT /api/admin/profile/notifications

    - Update: ReceiveUploadNotifications, ReceiveSyncFailureNotifications, NotificationFrequency

Frontend Team TODO

- [ ] Admin Profile Page (components/Admin/AdminProfile.jsx)

  - [ ] Display admin info

  - [ ] Notification preferences:

    - [ ] Checkbox: Receive upload notifications

    - [ ] Checkbox: Receive sync failure notifications

    - [ ] Dropdown: Immediate / Hourly Digest / Daily Digest

  - [ ] "Save" button

- [ ] Notification Preferences in Header

  - [ ] Add link to profile/settings in header

  - [ ] Quick toggle for notifications

Testing TODO

- [ ] Email Testing

  - [ ] Test new upload notification sent

  - [ ] Test email contains correct information

  - [ ] Test multiple admins receive email

  - [ ] Test notification preferences (admins can opt out)

  - [ ] Test email sent on sync failure

  - [ ] Load test: 50 uploads, verify all emails sent

- [ ] Phase 3 Complete Testing

  - [ ] Test admin login

  - [ ] Test admin can view all uploads

  - [ ] Test filtering and search

  - [ ] Test adding admin notes

  - [ ] Test moving files between projects

  - [ ] Test restoring deleted files

  - [ ] Test manual validation trigger

  - [ ] Test email notifications

  - [ ] Test notification preferences

  - [ ] Security test: ensure suppliers can't access admin routes

Phase 3 Complete: ✅ Admin system fully functional

Phase 3 Demo Checklist:

- [ ] Admin can log in

- [ ] Admin sees all supplier uploads

- [ ] Admin can filter and search uploads

- [ ] Admin can add notes and mark as reviewed

- [ ] Admin can move files between projects

- [ ] Admin can restore deleted files

- [ ] Admin receives email for new uploads

- [ ] Admin can update notification preferences

7. PHASE 4: Sync & Production Hardening (3 Weeks)

7.1 Phase 4 Objectives

- ✅ Implement Azure Files to Z:\FTProot sync

- ✅ Error handling and retry logic

- ✅ Performance optimization

- ✅ Security hardening

- ✅ Production deployment

7.2 Phase 4 Deliverables

- Sync service (Azure Files → Z:\FTProot)

- Comprehensive error handling

- Performance optimizations

- Security audit and fixes

- Production deployment

7.3 WEEK 15: Sync Service Implementation

Backend Team TODO

- [ ] Sync Service Architecture Decision

  - [ ] Option A: Azure File Sync (Microsoft's native solution)

    - Pros: Managed, automatic, bidirectional (we'll configure one-way)

    - Cons: Setup complexity, licensing

  - [ ] Option B: Custom Python/PowerShell script

    - Pros: Full control, simpler for one-way sync

    - Cons: Manual maintenance

  - [ ] Recommendation: Start with custom script, migrate to Azure File Sync if needed

- [ ] Custom Sync Service (if Option B chosen)

  - [ ] Create Windows Service or scheduled task on Z:\ server

  - [ ] sync_service.py:

  - # Run every 2 minutesdef sync_from_azure_to_z_drive():    # Get list of files changed since last sync (from SQL)    # For each changed file:    #   - Download from Azure Files    #   - Copy to Z:\FTProot maintaining folder structure    #   - Update SQL: SyncedToFTPRoot=TRUE, SyncTimestamp    # Log any errors

  - [ ] Use Azure Storage Python SDK to download files

  - [ ] Use Windows file copy for Z:\ write

  - [ ] Implement differential sync (only changed files)

  - [ ] Handle file conflicts (Azure always wins)

- [ ] Sync Tracking

  - [ ] Add to SupplierUploads table:

    - LastSyncAttempt (DATETIME)

    - SyncStatus (NVARCHAR: Success, Failed, Pending)

    - SyncErrorMessage (NVARCHAR)

  - [ ] Create SyncLog table:

  - CREATE TABLE SyncLog (    SyncID INT PRIMARY KEY IDENTITY(1,1),    UploadID INT FOREIGN KEY REFERENCES SupplierUploads(UploadID),    SyncStartTime DATETIME,    SyncEndTime DATETIME,    Status NVARCHAR(50),    FilesSynced INT,    ErrorMessage NVARCHAR(MAX));

- [ ] Retry Logic

  - [ ] Retry failed syncs 3 times with exponential backoff (1m, 5m, 15m)

  - [ ] After 3 failures, send email notification to admin

  - [ ] Mark sync as "ManualReviewRequired"

- [ ] Sync API Endpoints

  - [ ] GET /api/admin/sync/status

    - Return overall sync health

    - Last sync time, pending syncs, failed syncs

  - [ ] POST /api/admin/sync/retry/{uploadId}

    - Manually trigger sync retry

  - [ ] GET /api/admin/sync/logs

    - Return sync history with filters

DevOps TODO

- [ ] Install Sync Service on Windows Server

  - [ ] Deploy sync_service.py to \Vdbcwks0036

  - [ ] Create Windows scheduled task (runs every 2 minutes)

  - [ ] Configure logging to file and Azure Application Insights

  - [ ] Set up monitoring alerts for sync failures

- [ ] Network Configuration

  - [ ] Ensure server can access Azure Files (firewall rules)

  - [ ] Verify Z:\ drive permissions (service account has write access)

  - [ ] Test connectivity to Azure SQL from sync server

Testing TODO

- [ ] Test sync of single file

- [ ] Test sync of large project (1000+ files)

- [ ] Test sync with concurrent uploads

- [ ] Test sync failure scenarios (network down, Z:\ unavailable)

- [ ] Test retry logic

- [ ] Test sync status API

- [ ] Test manual sync trigger

- [ ] Verify folder structure matches on Z:\

Week 15 Milestone: Sync service functional and tested

7.4 WEEK 16: Error Handling, Optimization & Security

Backend Team TODO

- [ ] Comprehensive Error Handling

  - [ ] Add try-except blocks to all API routes

  - [ ] Return user-friendly error messages

  - [ ] Log detailed error info to Application Insights

  - [ ] Create error response format:

  - {  "error": true,  "message": "User-friendly message",  "code": "ERROR_CODE",  "details": "Technical details (only in dev)"}

  - [ ] Handle specific Azure errors (quota exceeded, network timeout, etc.)

- [ ] Performance Optimization

  - [ ] Add database indexes:

  - CREATE INDEX idx_uploads_supplier ON SupplierUploads(SupplierID);CREATE INDEX idx_uploads_date ON SupplierUploads(UploadCompleteTime);CREATE INDEX idx_filelog_upload ON FileOperationLog(UploadID);

  - [ ] Implement API response caching (Redis or in-memory)

  - [ ] Optimize file listing queries (pagination, limit returned fields)

  - [ ] Add database connection pooling

  - [ ] Optimize chunked upload assembly

- [ ] Rate Limiting

  - [ ] Implement rate limiting middleware:

    - 100 requests/minute per user

    - 5 OTP requests/hour per email (already done)

  - [ ] Use Redis for rate limit tracking

- [ ] Input Validation

  - [ ] Add validation for all API inputs (using Marshmallow or Pydantic)

  - [ ] Sanitize file names (prevent path traversal)

  - [ ] Validate file types (check MIME types, not just extensions)

  - [ ] Limit filename length (max 255 chars)

Frontend Team TODO

- [ ] Error Handling

  - [ ] Global error boundary component

  - [ ] User-friendly error messages (not stack traces)

  - [ ] Retry buttons for failed operations

  - [ ] Network offline detection

- [ ] Performance Optimization

  - [ ] Code splitting (lazy load routes)

  - [ ] Image optimization

  - [ ] Minify and bundle JS/CSS

  - [ ] Implement service worker for offline support (optional)

- [ ] Loading States

  - [ ] Skeleton screens for all data loading

  - [ ] Progress indicators for all async operations

  - [ ] Optimistic UI updates where appropriate

Security Team TODO

- [ ] Security Audit

  - [ ] OWASP Top 10 checklist

  - [ ] SQL injection testing (all inputs)

  - [ ] XSS testing (all outputs)

  - [ ] CSRF protection (add CSRF tokens)

  - [ ] JWT token security review

  - [ ] Azure storage access review (ensure no public access)

- [ ] Penetration Testing

  - [ ] Hire external security firm or use internal team

  - [ ] Test authentication bypass attempts

  - [ ] Test file access controls

  - [ ] Test API rate limits

  - [ ] Test for sensitive data exposure

- [ ] Security Hardening

  - [ ] Enable HTTPS only (redirect HTTP to HTTPS)

  - [ ] Set security headers:

    - Content-Security-Policy

    - X-Frame-Options: DENY

    - X-Content-Type-Options: nosniff

    - Strict-Transport-Security

  - [ ] Disable directory listing

  - [ ] Remove debug/error details in production

  - [ ] Implement logging of security events

Testing TODO

- [ ] Load testing (simulate 100 concurrent users)

- [ ] Stress testing (upload limits, database capacity)

- [ ] Security testing (penetration test results)

- [ ] Browser compatibility (Chrome, Firefox, Safari, Edge)

- [ ] Mobile responsiveness

Week 16 Milestone: System optimized, secured, and hardened

7.5 WEEK 17: Production Deployment & Final Testing

DevOps TODO

- [ ] Production Environment Setup

  - [ ] Create production Azure resources (separate from staging)

  - [ ] Configure production database (enable geo-replication)

  - [ ] Set up production Azure Files (with backup)

  - [ ] Configure Azure CDN (optional, for static assets)

  - [ ] Set up Azure Application Gateway / Load Balancer

- [ ] SSL/TLS Configuration

  - [ ] Purchase SSL certificate or use Azure-managed certificate

  - [ ] Configure custom domain: suppliers.vandyk.com

  - [ ] Force HTTPS

- [ ] Monitoring & Alerting

  - [ ] Configure Azure Monitor alerts:

    - API response time > 2 seconds

    - Error rate > 5%

    - Database DTU usage > 80%

    - Storage usage > 80%

    - Sync failures

  - [ ] Set up log analytics workspace

  - [ ] Create dashboards in Azure Portal

- [ ] Backup Strategy

  - [ ] Azure SQL automated backups (configured)

  - [ ] Azure Files snapshots (daily)

  - [ ] Database backup to separate storage account (weekly)

  - [ ] Document restore procedures

- [ ] Deployment Pipeline

  - [ ] Configure GitHub Actions for CI/CD:

  - # Deploy to staging on push to dev branch# Deploy to production on push to main branch (after approval)

  - [ ] Add smoke tests in deployment pipeline

  - [ ] Implement blue-green deployment or rolling updates

All Teams TODO

- [ ] User Acceptance Testing (UAT)

  - [ ] Invite 10 real suppliers to test system

  - [ ] Provide test projects and files

  - [ ] Collect feedback via survey

  - [ ] Fix any critical issues

- [ ] Documentation

  - [ ] Supplier User Guide:

    - How to log in

    - How to upload files

    - How to manage files

    - Troubleshooting common issues

  - [ ] Admin User Guide:

    - How to moderate uploads

    - How to move files

    - How to use reports

  - [ ] Technical Documentation:

    - System architecture diagram

    - API documentation (Swagger)

    - Database schema

    - Deployment guide

    - Runbook for common operations

    - Disaster recovery plan

- [ ] Training

  - [ ] Create training videos (5-10 minutes):

    - Supplier upload walkthrough

    - Admin portal walkthrough

  - [ ] Schedule live training sessions with Van Dyk staff

- [ ] Production Deployment Checklist

  - [ ] Code review all changes

  - [ ] Run full test suite (all tests passing)

  - [ ] Security audit complete

  - [ ] Performance testing complete

  - [ ] Backup production database before deployment

  - [ ] Deploy to production during low-traffic window

  - [ ] Monitor for 24 hours post-deployment

  - [ ] Have rollback plan ready

- [ ] Go-Live Preparation

  - [ ] Communication plan:

    - Email all suppliers about new portal

    - Include getting started guide

    - Announce go-live date

  - [ ] Support plan:

    - Dedicated support email: supplier-support@vandyk.com

    - On-call engineer for first week

    - Document common issues and solutions

Final Testing TODO

- [ ] End-to-End Production Testing

  - [ ] Test with real supplier accounts

  - [ ] Upload real project files

  - [ ] Test sync to Z:\FTProot

  - [ ] Test admin moderation

  - [ ] Test email notifications

  - [ ] Verify all logging and monitoring

- [ ] Performance Baseline

  - [ ] Record baseline metrics:

    - Average upload time (10GB file)

    - Average page load time

    - Average sync time

    - API response times

  - [ ] Set up ongoing monitoring against baselines

Week 17 Milestone: ✅ System deployed to production and go-live ready

8. Testing & Quality Assurance

8.1 Test Strategy

Unit Tests

- Backend: pytest for all services and routes (target: 80% coverage)

- Frontend: Jest + React Testing Library (target: 70% coverage)

Integration Tests

- API integration tests (test all endpoints)

- Database integration tests (test all queries)

- Azure Files integration tests (test file operations)

End-to-End Tests

- Selenium or Cypress for critical user flows:

  - Supplier login and upload

  - File management operations

  - Admin moderation workflow

Performance Tests

- JMeter or Locust for load testing

- Test scenarios:

  - 50 concurrent users

  - Upload 100 files simultaneously

  - 10,000 API requests in 1 minute

Security Tests

- OWASP ZAP automated scanning

- Manual penetration testing

- SQL injection testing

- XSS testing

8.2 Test Environments

| Environment | Purpose | Data |
| --- | --- | --- |
| Development | Developer local testing | Fake data |
| Staging | Pre-production testing | Anonymized prod data |
| Production | Live system | Real data |

8.3 Bug Tracking

- Use Jira/GitHub Issues for bug tracking

- Bug severity levels:

  - P0 (Critical): System down, data loss, security breach

  - P1 (High): Major feature broken, affecting multiple users

  - P2 (Medium): Minor feature issue, workaround available

  - P3 (Low): Cosmetic issue, no impact on functionality

9. Deployment Checklist

9.1 Pre-Deployment Checklist

- [ ] All tests passing (unit, integration, E2E)

- [ ] Code review completed

- [ ] Security audit completed

- [ ] Performance testing completed

- [ ] Documentation updated

- [ ] Backup of production database taken

- [ ] Rollback plan documented

- [ ] Communication sent to users (if needed)

9.2 Deployment Steps

- [ ] Merge feature branch to main

- [ ] GitHub Actions triggers deployment

- [ ] Deploy backend to Azure App Service

- [ ] Run database migrations

- [ ] Deploy frontend to Azure App Service

- [ ] Verify deployment (smoke tests)

- [ ] Update DNS (if needed)

- [ ] Monitor logs for 30 minutes

- [ ] Notify team of successful deployment

9.3 Post-Deployment Checklist

- [ ] Smoke tests pass

- [ ] Monitoring dashboards show normal metrics

- [ ] No critical errors in logs

- [ ] Test user can log in and upload

- [ ] Email notifications working

- [ ] Sync to Z:\FTProot working

- [ ] Admin portal accessible

- [ ] Update status page (if applicable)

9.4 Rollback Plan

If critical issue detected within 1 hour:

- Revert to previous version via GitHub Actions

- Restore database from backup (if schema changed)

- Notify users of downtime

- Investigate issue in staging

- Fix and re-deploy

10. Appendix: Technical Specifications

10.1 Database Schema (Complete)

-- Suppliers Table

CREATE TABLE Suppliers (

SupplierID INT PRIMARY KEY IDENTITY(1,1),

SupplierName NVARCHAR(200) NOT NULL,

SupplierType NVARCHAR(100) NOT NULL,

ContactEmail NVARCHAR(255) NOT NULL UNIQUE,

SecondaryEmails NVARCHAR(MAX),

AzureFolderPath NVARCHAR(500) NOT NULL,

CreatedDate DATETIME DEFAULT GETDATE(),

IsActive BIT DEFAULT 1,

LastLoginDate DATETIME

);

-- SupplierUploads Table

CREATE TABLE SupplierUploads (

UploadID INT PRIMARY KEY IDENTITY(1,1),

SupplierID INT FOREIGN KEY REFERENCES Suppliers(SupplierID),

SupplierEmail NVARCHAR(255),

ProjectNumber NVARCHAR(50) NOT NULL,

ProjectName NVARCHAR(200) NOT NULL,

FolderPath NVARCHAR(500),

UploadStartTime DATETIME,

UploadCompleteTime DATETIME,

FileCount INT,

TotalSizeMB DECIMAL(10,2),

HasManuals BIT,

HasInstallationDrawings BIT,

HasElectricalDrawings BIT,

ValidationReport NVARCHAR(MAX),

Status NVARCHAR(50) DEFAULT 'InProgress',

SyncedToFTPRoot BIT DEFAULT 0,

SyncTimestamp DATETIME,

LastSyncAttempt DATETIME,

SyncStatus NVARCHAR(50),

SyncErrorMessage NVARCHAR(MAX),

AdminModerated BIT DEFAULT 0,

AdminNotes NVARCHAR(MAX)

);

-- FileOperationLog Table

CREATE TABLE FileOperationLog (

OperationID INT PRIMARY KEY IDENTITY(1,1),

UploadID INT FOREIGN KEY REFERENCES SupplierUploads(UploadID),

SupplierID INT FOREIGN KEY REFERENCES Suppliers(SupplierID),

OperationType NVARCHAR(50) NOT NULL,

FileName NVARCHAR(500),

FilePath NVARCHAR(1000),

FileSize BIGINT,

PreviousVersionPath NVARCHAR(1000),

OperationTimestamp DATETIME DEFAULT GETDATE(),

PerformedBy NVARCHAR(255),

IsActive BIT DEFAULT 1

);

-- OTPTokens Table

CREATE TABLE OTPTokens (

TokenID INT PRIMARY KEY IDENTITY(1,1),

Email NVARCHAR(255) NOT NULL,

OTPCode NCHAR(6) NOT NULL,

CreatedAt DATETIME DEFAULT GETDATE(),

ExpiresAt DATETIME NOT NULL,

IsUsed BIT DEFAULT 0,

AttemptCount INT DEFAULT 0

);

-- AdminUsers Table

CREATE TABLE AdminUsers (

AdminID INT PRIMARY KEY IDENTITY(1,1),

Email NVARCHAR(255) NOT NULL UNIQUE,

FullName NVARCHAR(200),

ReceiveUploadNotifications BIT DEFAULT 1,

ReceiveSyncFailureNotifications BIT DEFAULT 1,

NotificationFrequency NVARCHAR(50) DEFAULT 'Immediate',

CreatedDate DATETIME DEFAULT GETDATE(),

IsActive BIT DEFAULT 1

);

-- SyncLog Table

CREATE TABLE SyncLog (

SyncID INT PRIMARY KEY IDENTITY(1,1),

UploadID INT FOREIGN KEY REFERENCES SupplierUploads(UploadID),

SyncStartTime DATETIME,

SyncEndTime DATETIME,

Status NVARCHAR(50),

FilesSynced INT,

ErrorMessage NVARCHAR(MAX)

);

-- Indexes

CREATE INDEX idx_uploads_supplier ON SupplierUploads(SupplierID);

CREATE INDEX idx_uploads_date ON SupplierUploads(UploadCompleteTime);

CREATE INDEX idx_filelog_upload ON FileOperationLog(UploadID);

CREATE INDEX idx_filelog_active ON FileOperationLog(IsActive);

CREATE INDEX idx_otp_email ON OTPTokens(Email);

10.2 API Routes Summary

Authentication

- POST /api/auth/request-otp - Request OTP for supplier

- POST /api/auth/verify-otp - Verify OTP and get JWT

- POST /api/auth/logout - Logout

- POST /api/admin/auth/request-otp - Request OTP for admin

- POST /api/admin/auth/verify-otp - Verify admin OTP

Supplier - Uploads

- POST /api/uploads/initiate - Start new upload

- POST /api/uploads/chunk/{uploadId} - Upload file chunk

- POST /api/uploads/complete/{uploadId} - Complete upload

- GET /api/uploads/status/{uploadId} - Get upload status

- GET /api/uploads/history - Get upload history

Supplier - Projects & Files

- GET /api/projects - List supplier's projects

- GET /api/projects/{projectId}/files - List files in project

- GET /api/projects/{projectId}/files/{fileId} - Get file metadata

- GET /api/projects/{projectId}/files/{fileId}/download - Download file

- GET /api/projects/{projectId}/download-all - Download project ZIP

- POST /api/projects/{projectId}/files/upload - Add files to project

- PUT /api/projects/{projectId}/files/{fileId} - Replace file

- DELETE /api/projects/{projectId}/files/{fileId} - Soft delete file

- GET /api/projects/{projectId}/files/{fileId}/versions - Get version history

- GET /api/projects/{projectId}/validation - Get validation results

- POST /api/projects/{projectId}/validate - Re-run validation

Admin

- GET /api/admin/uploads - Get all uploads (with filters)

- GET /api/admin/uploads/{uploadId} - Get upload details

- POST /api/admin/uploads/{uploadId}/moderate - Add admin notes

- GET /api/admin/uploads/{uploadId}/audit-trail - Get operation history

- POST /api/admin/files/move - Move files between projects

- POST /api/admin/files/{fileId}/restore - Restore deleted file

- POST /api/admin/uploads/{uploadId}/validate - Trigger validation

- POST /api/admin/sync/retry/{uploadId} - Retry sync

- GET /api/admin/sync/status - Get sync status

- GET /api/admin/sync/logs - Get sync logs

- GET /api/admin/stats - Get dashboard statistics

- GET /api/admin/profile/notifications - Get notification preferences

- PUT /api/admin/profile/notifications - Update notification preferences

10.3 Azure Resources Sizing

| Resource | Tier/Size | Monthly Cost (Est.) |
| --- | --- | --- |
| Azure App Service (Backend) | B2 (2 cores, 3.5GB RAM) | $73 |
| Azure App Service (Frontend) | B1 (1 core, 1.75GB RAM) | $54 |
| Azure SQL Database | Standard S2 (50 DTUs) | $150 |
| Azure Files Premium | 100GB provisioned | $13.65 |
| Azure Key Vault | Standard | $5 |
| SendGrid Email | 40k emails/month | $15 |
| Application Insights | 5GB ingestion | $10 |
| Total |  | ~$320/month |

Note: Costs vary by region and actual usage. Storage costs will increase with data growth.

10.4 Support & Maintenance Plan

Ongoing Tasks:

- Monitor Azure costs weekly

- Review logs daily for errors

- Update dependencies monthly (security patches)

- Database maintenance (reindex) monthly

- Storage cleanup (old deleted files) quarterly

- User feedback review monthly

- Feature requests prioritization quarterly

On-Call Rotation:

- Week 1 post-launch: 24/7 on-call

- Weeks 2-4: Business hours on-call

- Month 2+: Standard support (response within 4 hours)

11. Success Metrics & KPIs

11.1 Launch Metrics (First 3 Months)

| Metric | Target | Actual |
| --- | --- | --- |
| Suppliers onboarded | 20 |  |
| Total uploads | 100 |  |
| Average upload size | 2GB |  |
| System uptime | 99.5% |  |
| Average upload time (10GB) | < 30 min |  |
| Supplier satisfaction | 4.5/5 |  |
| Support tickets | < 50 |  |

11.2 Ongoing KPIs

- Uptime: 99.5%+ monthly

- Upload success rate: 98%+

- Sync success rate: 99%+

- Average response time: < 500ms

- Supplier adoption: 80% of suppliers using portal within 6 months

- Support ticket reduction: 80% reduction vs. previous manual process

12. Post-Launch Roadmap

Month 4-6: Enhancements

- [ ] Email notifications to suppliers (upload confirmation)

- [ ] Advanced search (full-text search in PDFs)

- [ ] Supplier analytics dashboard

- [ ] Mobile app (iOS/Android)

Month 7-12: Advanced Features

- [ ] OCR for automatic document classification

- [ ] Automatic drawing number extraction

- [ ] Approval workflow (Van Dyk review before making files available)

- [ ] Version comparison tool

- [ ] Commenting system (supplier-admin communication)

Document Prepared By: Van Dyk Engineering Team
Reviewed By: [Stakeholder Names]
Approved By: [Project Sponsor]
Date: October 10, 2025

READY FOR DEVELOPMENT ✅